## Slide 1: Milton DPW Yard Needs Assessment Study
Presentation to Milton Board of Selectmen

## Slide 2: Milton DPW Yard Needs Assessment Study
ARTICLE 17 in the 2014 Annual Town Meeting authorized funding to conduct a needs assessment project
By amendment, ARTICLE 17 added a provision that a citizens committee be established to develop the scope of the project and oversee the study process.
ARTICLE 17 states…
ARTICLE 17 To see what sum of money the Town will vote to appropriate for a feasibility study of potential uses of the DPW yard, so-called, on Randolph Avenue, including without limitation use to support cemetery, consolidated facilities, and park operations, to determine how said appropriation shall be raised, whether by transfer from available funds, borrowing under applicable provisions of law, or otherwise; and to act on anything relating thereto.
VOTED. The Town voted to appropriate the sum of $35,000 for the purposes set forth in this article and that to meet said appropriation the sum of $35,000 be raised from funds certified by the Department of Revenue as free cash; and that the Moderator be authorized to appoint a committee of five citizens of the Town for the purposes set forth in this article; and that said committee shall be authorized to expend said sum of $35,000 for the purposes set forth in this article; and that said committee shall report to the Board of Selectmen by December 15, 2014.
PASSED BY VOICE VOTE

## Slide 3
STUDY COMMITTEE MEMBERS
Stanley Genega – Chairman
Marie Theodat
Kevin Burke
John Driscoll
Marvin Gordon
EXOFICIO MEMBERS/STAFF ADVISORS –
  Joseph Lynch – Director of Department of Public Works
  Thomas McCarthy – Parks Commission
  William Ritchie – Director of Consolidated Facilities

## Slide 4: SUMMARY
CURRENT
  Office & Admin.
    4,587 S.F.
  Employee Work Facilities
    1,100 S.F.
  Work Shops & Material Storage
    1,766 S.F.
  Vehicle Maintenance
    4,100 S.F.
  Equip. Wash Area
    0 S.F.
  Veh. & Equip. Storage
    25,453 S.F.
  TOTAL
    37,006 S.F.
NEEDED
  Office & Admin.
    7,202 S.F.
  Employee Work Facilities
    5,127 S.F.
  Work Shops & Material Storage
    11,098 S.F.
  Vehicle Maintenance
    7,394 S.F.
  Equip. Wash Area
    1,591 S.F.
  Veh. & Equip. Storage
    40,079 S.F.
  TOTAL
    72,492 S.F.
The existing facilities provide approximately one-half of the square footage of space as what industry standards typically provide. In fact, every aspect of facility utilization falls grossly short of industry standards!

## Slide 5: FACTORS THAT DRIVE THE NEED FOR ADEQUATE FACILITIES
The Vehicle Storage facilities are undersized and are unable to efficiently support current operations, resulting in a large portion of the multi-million dollar fleet being stored outdoors. This impacts DPW response times during cold and inclement weather conditions. It also contributes to the rapid deterioration of high value Town owned equipment and increases vehicle maintenance costs.
The DPW Headquarters building is also undersized, lacks adequate office space, conference room, storage areas, and code compliant Men’s and Women’s toilets, and is neither handicapped accessible nor handicapped compliant.
The maintenance area is generally undersized and cannot fit the Fire Department ladder truck inside the maintenance bays.
The buildings and site have limited public accessibility.
The physical separation between buildings and departments makes it difficult for DPW/CFD/Parks management to maintain safety and monitor workforce activities.

## Slide 6: FACTORS THAT DRIVE THE NEED FOR ADEQUATE FACILITIES
Inadequate working environment, including:
  Poor ventilation
  Inadequate lighting
  Confined workshop areas
  Inadequate facilities for state mandated training
  Inadequate employee facilities for mustering, break-room, toilets, and lockers
These deficiencies directly impact operations and the efficiency of service that the DPW, CFD, and Parks Departments are able to provide to the town.

## Slide 7: INSERT DATA ON SERVICE LIFE AND INCREASED MAINTENANCE OF EQUIPMENT

## Slide 8: Criterion Issued to Consultant by Study Committee
House DPW, Park Operations and CFD at a single site at 629 Randolph Avenue.
Cemetery Department to stay at existing facility on the cemetery grounds
Establish traffic patterns that effectively separate civilian vehicles from operational vehicles and equipment
Utilize, to the extent feasible, as many of the existing buildings at 629 Randolph Avenue campus as is possible
  Three existing buildings to be utilized under the optimum reuse plan
    Existing Vehicle Maintenance Garage to be converted to two-story office/admin building
    Existing storage buildings to be converted to bathrooms, locker rooms, crew training, and lunch room
    Use the existing pre-engineered metal building as core element in future expanded vehicle/equipment storage garages

## Slide 9: PROPOSED ALTERNATIVES
In all, fourteen conceptual alternatives were initially generated.
The Project Team reviewed each alternative and eliminated the concepts which did not effectively meet the operational criteria established by the Committee.
Eight alternatives were presented to the DPW Yard Study Committee.
  A comparative list of advantages and disadvantages were presented for each alternative.
After completing a comprehensive assessment of the alternatives with the DPW Yard Study Committee, Scheme 3C was selected as the most desirable, cost effective and efficient concept.

## Slide 10: PROPOSED ALTERNATIVE selected by Study Committee
Paste copy of Alternative 3C –
Get format converted so it works!

## Slide 11: Sequence and Funding Alternatives for Project Implementation
Project implementation must minimize disruption of the current operational functions of the various departments. Given that, implementation of the preferred alternative plan included developing a phasing plan for design and construction. The Committee suggested two scenarios for a possible design and construction schedule:
The first considers the entire project being approved at Town Meeting and proceeding with design and construction under a single phase and a single contract.
The second anticipates three distinct phases, each approved at separate Town Meetings, and under separated design and construction contracts.

## Slide 12: Major Project Elements
Construction of a new pre-engineered metal building with partial masonry
wall finish and concrete protection wall for the vehicle storage area,
maintenance area, wash bay, and shop areas
Factory foam insulated architectural metal panel with improved exterior finish
system.
Renovation of existing single story block building with complete gut of interior
and new partition walls, doors, windows, and insulation on exterior walls
Re-skin of existing Vehicle Storage building, including roof and walls
Renovation of existing Vehicle Maintenance space to become two-story
Administration Area, with ADA compliant elevator and new stair towers
Primary industrial support equipment for vehicle maintenance operations
Site improvements, including storm water management and paving upgrades
New fuel island canopy and fuel pumps (reuse existing fuel tanks)
New Salt Shed
Contingency allowance for unanticipated design and construction costs, pending final design.

## Slide 13: Scheduling and Cost Estimate as a Single Phase / Single Project Contract
Estimated costs for new building construction, building renovations and site improvements are based on…
Costs of similar construction for which bid prices are available,
Supplemented cost data obtained from published sources.
Cost Assumptions…
The project will be publicly bid under Chapter 149 requirements
Prices are based on 2015 costs.
Cost projection account for one (1) year of cost escalation.
  Additional escalation factors should be included once the project time
  line has been established by the Town.
Design Period – 10 Months
Bid Period - 2 Months
Construction Period- 18 Months

## Slide 14: Implementation as a Single-Phased / Single-Contract Project Cost Estimate
New Construction
Admin. Employee Facilities $0.70 million
Shops $2.57 million
Vehicle Maintenece $1.25 million
Wash $0.50 million
Vehicle/Equipment Storage $5.30 million
Added Cost for Specialty Foundations $0.84 million
Elevator / Egress Stairs $0.18 million
TOTAL NEW CONSTRUCTION $11.34 million
Renovation
Full Office Renovation $1.40 million
Full Employee Facilities $ 0.42 million
Vehicle Maintenece $ - million
Shop Renovations $ - million
Storage Garage Renovations $0.48 million
Added Cost for Specialty Foundations $ - million
TOTAL RENOVATION COST $2.30 million

## Slide 15: Implementation as a Single-Phased / Single-Contract Project Cost Estimate (Continued)
Miscellaneous
Industrial Equipment $0.64 million
Fuel Systems $0.06 million
Mezzanines $0.52 million
Site Develpoment $2.18 million
Specialty Site Develpoment $0.25 million
Salt / Sand Shed $0.52 million
TOTAL Misc. Cost $4.17 million
Factoring Costs
Market Adjustment (2%) $0.36 million
Design Contingency (10%) $1.81 million Escalation - 1 Year (6% per year) $1,20 million
TOTAL Factoring Cost $ 3.37 million

## Slide 16: Implementation as a Single-Phased / Single-Contract Project Cost Estimate (Continued)
Owner's Soft Costs
A&E (design, bid, const.) $2.11 million
A&E Special Services $0.63 million
Owner's Project Managers Fee $0.85 million
Furnishings (FFE) $0.08 million
Communications /
Low Voltage Systems $0.04 million Temporary Facilities $0.25 million
Printing / Advertising $0.01 million
Legal Cost $0.03 million
Commissioning $0.03 million
Abatement $0.05 million
Ch 17 Test & Inspections $0.04 million
Construction Contingency (8%) $1.69 million
TOTAL SOFT COSTS $5.81 million

## Slide 17: Implementation as a Single-Phased / Single-Contract Project Cost Estimate (Continued)
TOTAL PROJECT ESTIMATED COST
TOTAL NEW CONSTRUCTION $11.34 million
TOTAL RENOVATION COST $2.30 million
TOTAL Misc. Cost $4.17 million
TOTAL Factoring Cost $3.37 million
TOTAL SOFT COSTS $5.81 million
TOTAL PROJECT ESTIMATED COST $26.99 million

## Slide 18: Implementation as a Phased Project
Phase I (Estimated duration: design and construction = 10 months):
Renovation of existing crew break-room, lockers, showers, and toilets
(approximately 2,400 square feet.)
Complete gut renovation of interior, replacement of partitions, finishes,
doors, windows, fixtures, and insulation at exterior walls.
Phase II (Estimated duration: design and construction = 24 months):
New Vehicle Storage garage (approximately 32,700 square feet.)
New Vehicle Maintenance building (approximately 6,000 square feet)
New Wash Bay (approximately 1,400 square feet) Salt Shed (approximately
6,000 square feet)
Re-skin of existing Vehicle Storage garage (approximately 6,000 square feet)

## Slide 19: Implementation as a Phased Project
Phase III (Estimated duration: design and construction = 18 months)
Renovation of existing Vehicle Maintenance facility to accommodate 2-story administration offices (approximately 8,000 square feet)
Complete gut renovated interior.
Cutting and patching of concrete slab
Infill of overhead door openings
Infill louvered openings as needed for HVAC and pressure ventilation
New partition walls, doors, windows, and insulation at exterior walls.
New egress stair and elevator towers
Shops Area (approximately 12,600 square feet) Employee Facilities
(approximately 2,400 square feet)
New fuel canopy and pumps (reuse existing fuel tanks)

## Slide 20: Scheduling and Cost Estimate as a Multi-Phase / Multi-Contract Projects
PHASE 1
Design Period – 2 Months
Bid Period - 2 Months
Construction Period- 6 Months
PHASE 2
Design Period – 8 Months
Bid Period - 2 Months
Construction Period- 14 Months
PHASE 3
Design Period – 6 Months
Bid Period - 2 Months
Construction Period- 10 Months

## Slide 21: Implementation as Three Multi-Phased / Multi-Contract Projects Cost Estimate

## Slide 22: Next Steps…